## Slide 1: CALL CENTER SURVEY PORTAL
Project Guide:- Asst. Prof. Meera K Chandran,
Department of Computer Applications,
SNGCE
Submitted by:- Amrutha Surendran,
S6 MCA,
Roll no:4,
SNGCE

## Slide 2: ABSTRACT
The call center survey portal project is a customer call center service management system. It handles customer survey for vehicle dealers. It is designed to replace an existing manual survey system for reducing time taken for calculation and for storing data. The system is storing the data to handle daily operation where the data base is cleared overtime. The system will reduce manual works, calculations and will also provide periodic reports at any time.
Modules:
1. User Management
2.Service Management
User Management include the user registration and their login.
Survey Management includes importing customers so that the admin can assign them to agents.

## Slide 3: SPRINT PLANNER- 4
ID | SPRINT | START DATE | END DATE | HOURS | SPRINT GOAL | ACCEPTANCE CRITERIA
1 | 1,2 | 15/1/2020 | 5/2/2020 | 90 hrs | Main user interface | Given I am a user, I want a main user interface so than I can do further activities
2.1 | 2,3 | 6/2/2020 | 19/2/2020 | 60hrs | Registration page for Region admin | Given I am an admin, I want to register region admin so that they can enter in to the system.
2.2 | 3,4 | 20/2/2020 | 4/3/2020 | 60 hrs | Registration page for dealers | Given I am an admin, I want to register dealer so that they can enter in to the system.
2.2 | 4,5 | 5/3/2020 | 18/3/2020 | 60 hrs | Registration page for dealers. | Given I am an admin, I want to register dealer so that they can enter in to the system.

## Slide 4
ID | SPRINT | START DATE | END DATE | HOURS | SPRINT GOAL | ACCEPTANCE CRITERIA
2.3 | 4,5 | 5/3/2020 | 18/3/2020 | 60 hrs | Registration page for agents | Given I am an admin, I want to register agents so that they can enter in to the system.
3 | 5,6 | 19/3/2020 | 8/4/2020 | 90 hrs | Login page for all users | Given I am an user, I want to login into so that i can enter in to the system.
4 | 7 | 9/4/2020 | 22/4/2020 | 60 hrs | Import customer details for survey | Given I am an agent, I want to import customer details so that i can take survey.

## Slide 5
Sprint | Start date | End date
4 | 27/02/2020 | 12/03/2020
Fid | Description | Status
2.2 2.3 | Registration page for dealers Registration page for agents | Fully completed

## Slide 6: Actual Burndown chart

## Slide 7: SPRINT PLANNER-5
ID | SPRINT | START DATE | END DATE | HOURS | SPRINT GOAL | ACCEPTANCE CRITERIA
1 | 1,2 | 15/1/2020 | 5/2/2020 | 90 hrs | Main user interface | Given I am a user, I want a main user interface so than I can do further activities
2.1 | 2,3 | 6/2/2020 | 19/2/2020 | 60hrs | Registration page for Region admin | Given I am an admin, I want to register region admin so that they can enter in to the system.
2.2 | 3,4 | 20/2/2020 | 4/3/2020 | 60 hrs | Registration page for dealers | Given I am an admin, I want to register dealer so that they can enter in to the system.
2.2 | 4,5 | 5/3/2020 | 18/3/2020 | 60 hrs | Registration page for dealers. | Given I am an admin, I want to register dealer so that they can enter in to the system.

## Slide 8
ID | SPRINT | START DATE | END DATE | HOURS | SPRINT GOAL | ACCEPTANCE CRITERIA
2.3 | 4,5 | 5/3/2020 | 18/3/2020 | 60 hrs | Registration page for agents | Given I am an admin, I want to register agents so that they can enter in to the system.
3 | 5,6 | 19/3/2020 | 8/4/2020 | 90 hrs | Login page for all users | Given I am an user, I want to login into so that i can enter in to the system.
4 | 7 | 9/4/2020 | 22/4/2020 | 60 hrs | Import customer details for survey | Given I am an agent, I want to import customer details so that i can take survey.

## Slide 9
Sprint | Start date | End date
5 | 13/03/2020 | 12/04/2020
Fid | Description | Status
4 | Login page for all users | Fully completed

## Slide 10: Actual Burndown chart

## Slide 11: Home page

## Slide 12: User Registration(Agent)

## Slide 13: User Registration(Dealer)

## Slide 14: User Registration(Region Admin)

## Slide 15: Login

## Slide 16: Forgot Password

## Slide 17: Recover Password